## template
CS673T2_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
example week | 5 | 4 | 1 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | 2 | [6 empty] | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6

## Gautam
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
example week | 5 | 4 | 1 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | 2 | [6 empty] | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6
Week 1 9/19 - 9/26 | 4.5 | 2 | 2.5 | 0 - Learned Git and got hands on with repository creation. 1 - Discussed modules, programming environments and division of tasks with team. 5 - Team meeting. | 2 | 1.5 |  |  |  | 2.5 |  | 0 - Learn reactjs, continue with git. 1 - Define project requirements after discussing with customer. 2 - Design structure of landing page. 3 - Implement landing page. 5 - Team meeting | 8
Week 2 9/26 - 10/3 | 8 | 4 | 4 | 0 - Learned Git further, learned meteorjs 1 - worked on SPPP, defined project requirements after discussion 3 - Cloned git project, Created separate git branch to work on 5 - team meeting | 2 | 1.5 |  | 0.5 |  | 4 |  | 0 - continue learning meteorjs 2 - begin creating structure of landing page 3 - implement landing page 5 - Team meeting | 7
Week 3 10/3 - 10/10 | 6 | 4 | 2 | 0 - Learned meteorjs 1 - Figured out stories for messaging 3 - got latest code version to run on machine, played around a bit. 5 - Team Meeting | 1.5 | 1.5 |  | 1 |  | 2 |  | 0 - Continue to improve skills in meteorjs 1 - Complete stories for messaging 3 - Start coding on messaging 5 - Team meeting | 8
Week 4 10/10 - 10/17 | 8 | 5 | 3 | 0 - Continued meteorjs 1 - Worked on stories for messaging 3- Began coding on messaging 5- Team meeting | 2 | 2 |  | 1 |  | 3 |  | 0 - Master meteorjs for project 1 - Complete stories for my part 3 - Continue implementation on backend 5- Team meeting | 8
Week 5 10/17 - 10/24 | 8 | 5 | 3 | 0 - Continued meteorjs, started mongoDB 3 - Continued coding APIs for messages story 5- Team meeting | 3 |  |  | 2 |  | 3 |  | 0 - Finish meteorjs and mongodb 2 - SDD 3 - Continue implementation 5 - Team meeting | 10
Week 6 10/24 - 10/31 | 8 | 5 | 3 | 0 - Continued meteorjs backend 2 - Worked on SDD 3 - Continued Coding APIs 5 - Team Meeting | 1 |  | 1 | 3 |  | 3 |  | 0 - Refer to meteor docs when necessary 2 - SDD 3 - Continue API implementation 5 - Team Meeting | 8
Week 7 10/31 - 11/7 | 7 | 5 | 2 | 0 - Meteorjs documentation 2 - Worked on SDD 3 - Continued API Implementation 5 - Team Meeting | 1 |  | 2 | 2 |  | 2 |  | 0 - Refer to meteor docs when necessary 2 - SDD 3 - Continue API implementation 5 - Team Meeting | 8
Week 8 11/7 - 11/14 | 8 | 5 | 3 | 0 - Meteor docs & videos 2 - SDD 3 - APIs for messaging 5- Team Meeting | 1 |  | 3 | 1 |  | 2 |  | 3 - Generate documentation, emojis for messaging, better database design 5 - Team meeting | 8
Week 9 11/14 - 11/21 | 5.5 | 4.5 | 1 | 0 - emojiOne & meteor docs (for integration) 2 - SDD, reviewed database design 3 - code for emojis 5 - Team meeting | 1.5 |  | 2 | 1 |  | 1 |  | 0 - Learn whenever necessary 2 - Update database desgin if needed 3 - Try and implement all stories 5 - team meeting | 8
Week 10 11/21 - 11/28 | 4 | 4 | 0 | 0 - Learning 2 - Updated Database Design | 2 |  | 2 |  |  |  |  | 0 - Learn whenever necessary 2 - Update database desgin if needed 3 - Try and implement all stories 5 - team meeting | 7
Week 11 11/28 - 12/5 | 5 | 3 | 2 | 0 - Tried to learn about emoji libraries in meteor 3 - Continued implementation 5 - Team Meeting | 1 |  |  | 2 |  | 2 |  | 0 - Learn whenever necessary 3 - Continue implementing stories 5 - Team meeting | 6
Week 12 12/5 - 12/12 | 17 | 13 | 4 | 0 - Learned and failed at emojis 3 - Deployed app on digitalocean 3 - Continued implementation 4 - Wrote tests 5 - Meeting | 2 |  |  | 10 | 1 | 4 |  | 6 - Wrap things up!
Week 13 12/12 - 12/19 | 2 | 2 | 0 | 6 - Documentation updates | [6 empty] | 2

## Bella
CS673T2_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
example week | 5 | 4 | 1 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | 2 | [6 empty] | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6
(09/19-09/26) | 5.5 | 3 | 2.5 | 0 - learning meteor 5 - team meeting | 2 |  |  |  |  | 3 |  |  | 5
(09/27-10/2) | 7 | 4 | 3 | 0 - tutoring and discuss sppp 5 - team meeting | 3 |  |  |  |  | 3 |  |  | 6
(10/3-10/10) | 7 | 5 | 2 | 0 - learning 1 - requirement analysis 2 - design 5 - team meeting | 1 | 1 | 2 |  |  | 3 |  |  | 7
(10/4-10/17) | 8 | 5 | 3 | 0 - Continue learning meteor.js 1 - discussion on diagram and functions 3 - start working on profile page to add alias function 5 - team meeting | 1 | 0.5 | 3.5 |  |  | 3 |  |  | 8
(10/18-10/24) | 8 | 5 | 3 | 0 - Learning meteor.js 3 - working on profile pages 5 - team meeting | 3 |  | 2 |  |  | 3 |  |  | 8
(10/25-10/31)

## Ian
CS673T2_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
example week | 5 | 4 | 1 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | 2 | [6 empty] | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6
Week #0 (9/12/16) | 3.5 | 1 | 2.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #1 (9/19/16) | 4 | 1 | 3 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #2 (9/26/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #3 (10/3/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #4 (10/10/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #5 (10/17/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #6 (10/24/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #7 (10/31/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #8 (11/7/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #9 (11/14/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #10 (11/21/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #11 (11/28/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #12 (12/5/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting
Week #13 (12/12/16) | 5 | 2 | 1.5 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | [7 empty] | 0 - learning git, django 1 - discuss project requirement 5 - team meeting

## Gabe
CS673T2_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
example week | 5 | 4 | 1 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | 2 | [6 empty] | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6
Week 1 (09/19-09/26) | 6 | 3.5 | 2.5 | 0 - learning meteor 1 - requirement analysis 5 - team meeting | 3 | 0.5 |  |  |  | 2.5 |  | 0 - continue learning meteor 5 - team meeting 1 - work on SPPP | 6
Week 2 (9/26/16 - 10/3/16) | 8 | 5 | 3 | 0 - learning meteor 0 - learning GIT 1 - SPPP, discuss project requirements, create presentation for SPPP 5 - team meeting | 3 | 2 |  |  |  | 3 |  | 0 - research meteor security and learn it more 1 - write stories for application reqs 1 - write analysis of security for meteor app
Week 3 (10/3-10/10) | 6 | 4 | 2 | 0 - learning meteor 0 - learning GIT 1 - requirement analysis - research security 5 - team meeting | 1.5 | 2.5 |  |  |  | 3 |  | 1 - update SPPP with some security documenation 2 - analyze how to best create fake users for task assigned | 7
Week 4 (10/10-10/17) | 6 | 2 | 2 | 0 - Git tutorials 1 - Security document 5 - team meeting | 2 | 2 | 2 |  |  |  |  | Continue to learn meteor | 8
Week 5 (10/18-10/24) | 6 | 5 | 3 | 0 - Learning meteor.js 3 - working on profile pages 5 - team meeting | 3 |  | 2 |  |  | 3 |  | 0 - more learning | 8
Week 6 (10/25-10/31) | 6.5 | 3.5 | 3 | 0 - Learning meteor.js 0 - team workshops / team motivation 3 - research facebook integration 5 - team meeting | 2.5 |  |  | 2 |  | 2 |  | 0 - more learning & documentation | 6
Week 7 (11/1-11/07) | 6 | 3 | 3 | 0 - GIT tutorial 3 - Reviewing existing code 5 - team meeting | 2 |  |  | 2 |  | 2 |  | 0 - do more git tutorials for command line 2 - update sddd 3 - make one to two code changes | 6
Week 8 (11/7 - 11/14) | 9 | 5 | 4 | 0 - learning about react (reading, code review) 2 - Update SDDD 3 - landing page update 3 - discover page updates 5 - team meeting | 2 |  | 1 | 2 |  | 4 |  | 0 - more react and meteor learning 0 - more security reading and documentation/user story creation 3 - update discover page 5 - meetings | 8
Weeks 9-10 (11/15-12/3) | 16 | 12 | 4 | 0 - Watch security Meteor/Mongo videos 0 - git command tutorials 0 - static code analysis articles 0 - meteor security articles and videos 3 - Update code to add esLint code scanner plugin 3 - Update code to add static analysis tool & run scan 3 - update code to correct test case 3 - Update code to add text to profile editing 2 - Security powerpoint on meteor 2- took over as requirements leader from bella - created stories in pivotal tracker to improve our story backlog and use proper story format: -created enhancement stories for discover page -created stories for existing functionality where no story had existed yet even though code work was done for the story | 4 | 3 | 5 |  |  | 4 |  | 0 - more videos and tutorials 0 - further improve code 0 - create more requirements/stories
Week 11 (12-4 to 12/8) | 16 | 12 | 4 | 0 - Read meteor and mongo documentation on autopublish,etc 0 - Read on security for OAuth 3 - Update code to remove autopublish, insecure packages 3 - Create meteor methods - refactoring for security 3 - Add publish/subscribe model - refactoring for security 3 - Refactor code to add checks for data type safety to prevent injection 3 - Other code refactoring for readability, separation of concerns 2 - Security powerpoints - OAuth slide, Use case slide, Security Slides for ppt | 4 |  | 2 | 6 |  |  |  | Upload docs to github, update security doc
Week 12 (12/9-12/15) | 3 |  |  | 3 - Work with Daniel to merge my code 2 - Update Security Document 2 - Upload Security document to github |  |  | 2 | 1 |  |  |  | relax!

## Becky
CS673T2_weeklyreport_rbell
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
example week | 5 | 4 | 1 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | 2 | [6 empty] | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6
1 (09/19-09/26) | 5.5 | 3 | 2.5 | 0 - learning meteor 5 - team meeting, project chat | 3 |  |  |  |  | 3 |  | 0 - continue learning meteor 5 - team meeting | 6
2 (9/26 - 10/3) | 6 | 1 | 3 | 0 - learning meteor, github refresh 1 - requirement documentation 5 - team meeting | 2 | 1 |  |  |  | 3 |  | 0 - meteor/node review 1 - requirement revision 3 - profile page work 5 - team meeting | 6
3 (10/3 - 10/10) | 5 | 3 | 2 | 0 - learning meteor 3 - experimenting with app 5 - team meeting | 2 |  |  | 1 |  | 2 |  | 0 - react.js research 2 - look at user profile design 3 - user profile tweaks 5 - team meeting | 7
4 (10/10 - 10/17) | 7 | 2 | 3 | 0 - react.js research 1 - writing user stories 3 - user profile work 5 - team meeting |  | 1 |  | 2 |  | 4 |  | 0 - react.js research 3 - user profile work 4 - testing 5 - team meeting | 8
5 (10/17 - 10/24) | 5 | 2 | 3 | 3 - user profile work 5 - team meeting |  |  |  | 2 |  | 3 |  | 3 - coding 4 - testing | 8
6 (10/24 - 10/31) | 6.5 | 2 | 3.5 | 0 - react.js research 3 - user profile work 5 - team meeting | 1 |  |  | 1 |  | 4.5 |  | 0 - react.js research 3 - user profile work 5 - team meeting | 6
7 (10/31 -11/7) | 7 | 3 | 3 | 0 - react.js research 3 - user profile work 5 - team meeting | 1 |  |  | 2 |  | 4 |  | 0 - react.js research 3 - user profile work 5 - team meeting | 6
8 (11/7 - 11/14) | 8 | 4 | 3 | 0 - react.js, materialize css research 3 - user profile work 3 - discover page work 5 - team meeting | 1 |  |  | 3 |  | 4 |  | 0 - react.js, materialize css research 3 - user profile work 3 - discover page work 5 - team meeting | 8
9 (11/14 - 11/21) | 2 | 1 | 1 | 0 - testing strategies 3 - profile page work 6 - PR reviews 5 - team meeting | 1 |  |  |  |  | 1 |  | 3 - user profile work 3 - discover page work 5 - team meeting | 6
10 (11/21 - 11/28) | 3 | 3 | 0 | 5 - team comm/mentoring/meeting 6 - PR reviews | [5 empty] | 2 | 1 | 0 - testing research 3 - user profile work 5 - team meeting | 6
11 (11/28 - 12/5) | 5 | 2 | 2 | 5 - team comm/mentoring/meeting 6 - PR reviews | [5 empty] | 4 | 1 | 3 - user profile work 5 - team meeting | 6
12 (12/5 - 12/12) | 9 | 5 | 4 | 3 - coding 4 - manual testing 5 - team comm/mentoring/meeting 6 - PR reviews |  |  |  | 2 | 2 | 6 | 1 | 6 - documentation updates | 3
12/12 - 12/19 | 2 | 2 | 0 | 6 - documentation updates & uploading | [6 empty] | 2
Wooo, we made it!

## Daniel
CS673T2_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
example week | 5 | 4 | 1 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | 2 | [6 empty] | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6
Week1 (09/19-09/26) | 7.5 | 5 | 2.5 | 0 - learning meteor 2 - design 5 - team meeting, project chat | 3 | 2 |  |  |  | 3 |  | 0 - continue learning meteor 5 - team meeting | 7
Week2 (9/26 - 10/3) | 11 | 9 | 3 | 0 - learning meteor 1 - requirement documentation 2 - design 3 - implementation 5 - team meeting | 1 | 2 | 3 | 3 |  | 3 |  | 1-requirement analysis 2 - design | 8
Week3 (10/4 - 10/10) | 7 | 5 | 2 | 1 - requirement documentation 2 - design 3 - implementation 5 - team meeting | 0 | 2 | 3 | 3 |  | 3 |  | 1-requirement analysis 2 - design | 7
Week4 (10/11 - 10/17) | 7 | 5 | 2 | 1 - requirement documentation 3 - implementation 5 - team meeting | 0 | 2 | 0 | 3 |  | 3 |  | 3 - implementation 5 - team meeting | 6
Week5 (10/18 - 10/23) | 5 | 3 | 2 | 1 - requirement documentation 3 - implementation 5 - team meeting | 0 | 2 | 0 | 3 |  | 3 |  | 3 - implementation 5 - team meeting | 6
Week6 (10/24 - 10/31) | 7 | 4 | 3 | 1 - requirement documentation 3 - implementation 5 - team meeting | 0 | 2 | 0 | 3 |  | 3 |  | 3 - implementation 5 - team meeting | 6
Week7 (11/1 - 11/7) | 7 | 4 | 3 | 1 - requirement documentation 3 - implementation 5 - team meeting | 0 | 2 | 0 | 3 |  | 3 |  | 3 - implementation 5 - team meeting | 6
Week8 (11/7 - 11/14) | 8 | 4 | 3 | 0 - react.js, materialize css research 3 - user profile work 3 - discover page work 5 - team meeting | 1 |  |  | 3 |  | 4 |  | 0 - react.js, materialize css research 3 - user profile work 3 - discover page work 5 - team meeting | 8
Week 9 (11/14 - 11/ 20) | 5.5 | 4.5 | 1 | 0 - Message Page 2 - SDD, reviewed database design 3 - code for emojis 5 - Team meeting | 1.5 |  | 2 | 1 |  | 1 |  | 0 - Learn whenever necessary 2 - Update database desgin if needed 3 - Try and implement all stories 5 - team meeting | 10
Week 10 11/21 - 11/28 | 7 | 5 | 2 | 0 - Learning 2 - Discover page grid | 2 | 2 | [5 empty] | 0 - Learn whenever necessary 2 - Update database desgin if needed 3 - Try and implement all stories 5 - team meeting | 10
Week 11 11/28 - 12/5 | 6 | 4 | 2 | 0 - learn more about noSQL database 3 - Continued implementation 5 - Team Meeting | 1 |  |  | 2 |  | 2 |  | 0 - Learn whenever necessary 3 - Continue implementing stories 5 - Team meeting
Week 12 12/5 - 12/12 | 17 | 13 | 4 | 0 - Learn testing 3 - Deployed app on digitalocean 3 - Continued implementation 4 - Wrote tests 5 - Meeting | 2 |  |  | 10 | 1 | 4 |  | 6 - Wrap things up!
Week 13 12/12 - 12/19 | 3 | 3 | 1 | 6 - Documentation updates | [6 empty] | 2

## Adiba
CS673T2_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
example week | 5 | 4 | 1 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | 2 | [6 empty] | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6
Week 1 (09/19-09/26) | 5.5 | 3 | 2.5 | 0 - learning meteor 5 - team meeting | 3 |  |  |  |  | 3 |  | 1-discussing requiremnts | 6
Week 2 (9/26/16 - 10/3/16) | 7 | 2 | 5 | Task Breakdown 0 - learning meteor, git 2 - design 5 - team meeting | 2 |  | 1 |  |  | 5 |  | 0-completing meteor and git tutorial | 6
Week 3 (10/3-10/10) | 6 | 3 | 3 | 0- learning meteor 1 - learning GIT 3 - team meeting | 3 |  |  |  |  | 3 |  | 0-learning react Js | 6
Week 4(10/11-10/17) | 6 | 3 | 3 | 0-Learning React JS 2-discussion on design and diagrams 3-Team Meeting | 2 |  | 1 |  |  | 3 |  | 0-Completing React JS 1-Working on requirement for Discover Page | 6
Week 5(10/17-10/23) | 7 | 4 | 3 | 0-completed React JS 1-Requirement for Discover Page 2-discussion on design and diagrams 3-Team Meeting | 2 | 1 | 1 |  |  | 3 |  | 3-Working on Discover Page | 6
Week 6(10/24-10/30) | 8 | 4 | 4 | 0-Understanding the entire code 3-Working on discover page 4-Creating Message PoputTest case 5-Team meeting | 1 |  |  | 2 | 1 | 4 |  | 0-Understanding the entire code 3-Working more on discover page 4-Completing Message PoputTest case 5-Team meeting | 7
Week 7(10/30-11/6) | 10 | 7 | 3 | 0-Understanding code 3-Implemented changes to discover page and commiitted to git 4-Tested the Popout test 5-team meeting | 1 |  |  | 4 | 2 | 3 |  | 0-Understanding code 2-Work on SDD 3-Implement more changes and create new pull requests 4-Test tutorial 5-team meeting | 7
Week 8(11/6-11/13) | 6 | 3 | 3 | 0-learninng 2-making chnages to SDD 4-Working on testing and tetsing tutorial 5-team meeting | 1 |  |  | 1 | 1 | 3 |  | 4-Implement more test cases. | 7
Week 9(11/14-11/20) | 6 | 4 | 2 | "0-Learning Acceptance testing 0-Selenium testing 2-making changes to SDD 4-Working on testing 5-Team meeting" 6-Updating meeting doc, keepin track of meeting minutes | 2 |  | 1 |  | 1 | 2 |  | 0-Learning Acceptance testing 0-Selenium testing 2-making changes to SDD 2-Designing Flow Diagrams for entire app 4-Working on Discover grids 4-Working on unit test controller 5-Team meeting | 10
Week 10(11/21-11/27) | 10 | 6 | 4 | 0-learning acceptance testing 3-Implemented grids for discover page and commited to git. 4-Working on testing 5-team meeting | 1 |  | 6 | 1 |  | 4 |  | 0-completing the acceptance tetsing 3-Implement test cases 4-Work on flow diagrams | 6
Week 11(11/28-12/04) | 8 | 4 | 4 | 0-learning acceptance testing 2-Designing all the flow diagrams to explain basic flow of Meetcute 4-Working on some code change to update the test case and some basic errors 5-team meeting | 1 |  | 2 |  | 1 | 4 |  | 0-learning acceptance testing 3-Implementing few test cases as part of acceptance testing 5-team meeting | 8
Week 12(12/05-12/12) | 8 | 4 | 4 | 0-learning acceptance testing 2-Designing the remaining flow diagrams to explain message flow of Meetcute 4-Working on some code change to update the test case and some basic errors 4-Working on slides 5-team meeting | 1 |  | 1 |  | 2 | 4 |  | 0-learning acceptance testing 3-Implementing few test cases as part of acceptance testing 5-team meeting | 8